## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | 1 | Setup Python environment,database, and understand multiprocessing concepts | MUST HAVE | - | Sriveni Bingi | 3- Completed
Sprint 1 | Sprint1 | 2 | Plan Text handling workflow and define data structures | MUST HAVE | 1 | Sriveni Bingi | 3- Completed
Sprint 2 | Sprint 2 | 3 | Implement Text Breaker and Loader using Parallel Processing (Chucking text) | MUST HAVE | 2 | Sriveni Bingi | 3- Completed
Sprint 2 | Sprint 2 | 4 | Apply pattern matching for initial filtering of text data | MUST HAVE | 3 | Sriveni Bingi | 3- Completed
Sprint 3 | Sprint 3 | 5 | Implement Rule checker for sentiment scoring using rule-based approach | MUST HAVE | 4 | Sriveni Bingi | 3- Completed
Sprint 3 | Sprint 3 | 6 | Implement Search Checker and CSV file saving functionality | MUST HAVE | 5 | Sriveni Bingi | 3- Completed
Sprint 4 | Sprint 4 | 7 | Store processed text and sentiment results in database | MUST HAVE | 5 | Sriveni Bingi | 3- Completed
Sprint 5 | Sprint 5 | 8 | Improve text storage and optimize retrieval performance | SHOULD HAVE | 7 | Sriveni Bingi | 3- Completed
Sprint 6 | Sprint 6 | 9 | Optimize performance and finalize system with UI & visualization | MUST HAVE | 9 | Sriveni Bingi | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 63 | 12 | 11 | 10 | 13 | 10 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US1 | T1 | Setup Python environment | 2026-02-09 | 2026-02-11 | Sriveni Bingi | Build | 3- Completed | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US1 | T2 | Install libraries | 2026-02-11 | 2026-02-12 | Sriveni Bingi | Build | 3- Completed | 3 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US1 | T3 | Database setup | 2026-02-13 | 2026-02-14 | Sriveni Bingi | Build | 3- Completed | 5 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG
US2 | T1 | Text chunking | 2026-02-15 | 2026-02-17 | Sriveni Bingi | Coding | 3- Completed | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US2 | T2 | Parallel Processing | 2026-02-18 | 2026-02-19 | Sriveni Bingi | Coding | 3- Completed | 4 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US2 | T3 | Testing chunking | 2026-02-20 | 2026-02-20 | Sriveni Bingi | Coding | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 3 BACKLOG
US3 | T1 | Design sentiment rules | 2026-02-21 | 2026-02-22 | Sriveni Bingi | Design | 3- Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US3 | T2 | Sentiment scoring | 2026-02-23 | 2026-02-25 | Sriveni Bingi | Coding | 3- Completed | 6 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 4 BACKLOG
US4 | T1 | DB integration | 2026-02-27 | 2026-03-01 | Sriveni Bingi | Build | 3- Completed | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US4 | T2 | CSV export | 2026-03-02 | 2026-03-04 | Sriveni Bingi | Coding | 3- Completed | 4 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 5 BACKLOG
US5 | T1 | Search feature | 2026-03-05 | 2026-03-07 | Sriveni Bingi | Coding | 3- Completed | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US5 | T2 | Storage optimization | 2026-03-08 | 2026-03-10 | Sriveni Bingi | Coding | 3- Completed | 5 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 6 BACKLOG
US6 | T1 | Streamlit UI | 2026-03-11 | 2026-03-13 | Sriveni Bingi | Coding | 3- Completed | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US6 | T2 | Testing & debugging | 2026-03-14 | 2026-03-16 | Sriveni Bingi | Coding | 3- Completed | 5 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Python environment variables not properly configured | Reachecked system paths , reinstalled Anaconda
Sprint 1 | Day 2 | Conflicts in Python libraries | Updated library versions, ensured virtual environment isolated
Sprint 1 | Day 3 | Setup incomplete, unsure if all dependencies are working | Verified environment and tested sample scripts
Sprint 1 | Day 4 | Libraries installation failed for some packages | Manually installed missing packages and resolved dependency conflicts
Sprint 1 | Day 5 | Database setup script failed due to missing files | Created database files and verified schema setup
Sprint 1 | Day 6 | Database connection errors | Closed previous sessions, reconnected, and tested queries
Sprint 2 | Day 7 | Chunking logic not splitting text correctly | Added debug prints and verified chunk sizes
Sprint 2 | Day 8 | Parallel processing throwing errors | Added try-except handling and debug logs for worker processes
Sprint 2 | Day 9 | Chunking test failed due to missing sample data | Created test dataset and re-ran tests
Sprint 3 | Day 10 | Sentiment rule design unclear for edge cases | Reviewed examples and adjusted scoring rules
Sprint 3 | Day 11 | Sentiment scoring function returned incorrect results | Debugged scoring logic, added validation for unknown words
Spritn 3 | Day 12 | Scoring function slow for large dataset | Optimized loops and vectorized calculations
Sprint 4 | Day 13 | DB integration caused connection errors | Verified DB path, handled open cursors correctly
Sprint 4 | Day 14 | CSV export failed for empty datasets | Added validation and tested export on sample data
Sprint 5 | Day 15 | Search feature not returning expected results | Debugged search query logic, updated indexing
Sprint 5 | Day 16 | Storage optimization logic not saving all files | Added chunked writing and verified storage paths
Sprint 6 | Day 17 | Streamlit UI widgets not rendering properly | Fixed widget configuration and layout issues
Sprint 6 | Day 18 | Streamlit UI lag on large datasets | Implemented caching and chunk-based display
Sprint 6 | Day 19 | Testing & debugging found errors in parallel processing | Fixed thread handling and added unit test
Sprint 6 | Day 20 | Testing & debugging found inconsistent sentiment results | Updated word lists and added input validation

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-02-09 | 2026-02-14 | Sriveni Bingi | Document environment setup steps for future reference | Manually fixing librar conflicts without recording steps | Verify environment setup before starting tasks | Created a checklist for Python environment and library installation
2 | Sprint 2 | 2026-02-15 | 2026-02-20 | Sriveni Bingi | Add debug logs early in code for chunking & parallel processing | Ignoring small errors until later | Follow daily stand-up reporting for blockers | Implemented logging in chunking and multiprocessing tasks
3 | Sprint 3 | 2026-02-21 | 2026-02-25 | Sriveni Bingi | Create test datasets for sentiment scoring | Testing only at the end of module | Follow iterative testing after completing each function | Generated sample datasets and ran scoring tests daily
4 | Sprint 4 | 2026-02-27 | 2026-03-04 | Sriveni Bingi | Plan DB integration with proper connection handling | Leaving cursors open causing SQLite Locked errors | Continue documenting solutions for DB issues | Closed cursors properly and verified DB connections
5 | Sprint 5 | 2026-03-05 | 2026-03-10 | Sriveni Bingi | Optimize storage and search logic ealier in sprint | Delaying optimization until end | Continue implementing features with incremental testing | Implemented search & storage optimization early and tested incrementally
6 | Sprint 6 | 2026-03-11 | 2026-03-16 | Sriveni Bingi | Plan pending features earlier in sprint and allocate time for testing | Delaying important features to last stage of sprint | Continue regular testing and debugging after each module | Completed Streamlit UI, fixed bugs during testing .
7 | Overall | 2026-02-09 | 2026-03-16 | Sriveni Bingi | Track impediments daily for quicker resolution | Waiting for problems to pile up | Continue using stand-ups to track progress | Manintained a daily log of blockers and actions taken